Point of Contact: Jeffrey S. Lesko, Principal/ Federal Programs Coordinator

POC Phone & Email:  724-295-9510 lesko@freeport.k12.pa.us    Team Members: Jeffrey Lesko, Michael Kleckner, Don Dell, Tim Walters, Aimee Raber- Campbell , Emily Lampus, Autumn Wyant Palmiter, Sarah Vivian , Renee Bogan, Angie Zollinger, Kelly Herbert

| TRANSITION ACTIVITY | ACTION STEPS | PERSON(S) RESPONSIBLE | TIMELINE - Begin | TIMELINE – Complete |
| --- | --- | --- | --- | --- |
| Continue to establish a communication network | Update lists and contact information of area preschool and daycare facilities; continue working with Early Learning Connections and ARIN Early Intervention | Building principals | Fall 2023 | Fall 2024 |
| Develop a Calendar of Activities for distribution to child care facilities, preschools, and FASD elementary families | Committee members will develop the calendar in June 2023 and refine it during the early fall of 2023 Distribute the calendars to local child care facilities and preschools, and request that they be given to FASD parents Provide calendars in the elementary schools for distribution to parents who register their children in the summer | Committee members Building principals | June 2023 | August 2023 |
| Collect “gently used” children’s books to distribute at Kindergarten Orientation | Inform elementary principals, PTO presidents, and local child care directors about this project Request elementary schools child care centers, and local libraries to contribute books | Elementary principals’ and PTOs’ support Communication with district parents and staff | Summer 2023 | Summer 2023 |
| TRANSITION ACTIVITY | ACTION STEPS | PERSON(S) RESPONSIBLE | TIMELINE - BEGIN | TIMELINE - COMPLETE |
| Publicize Kindergarten Registration | Communicate via *Individual school e-links *Letters/emails to District families *District website *Local newspapers *Posters in district buildings/preschools/day cares *Social media | Building Principals IT Coordinator Admin Office Building Secretaries | January 2024 | March 2024 |
| Conduct two forums for parents of FASD pre-kindergartners. The forum will be comprised of local child care and preschool directors/teachers and FASD kindergarten teachers, principals, etc., to inform parents about the kindergarten program and readiness activities | Discuss/Plan the process with the elementary principals Invite the local child care directors to participate in the forum. Publicize and schedule the forum Conduct the forum in March/April 2024 | Elementary principals Kindergarten teachers | Promotion to begin in February 2024 | March/April 2024 |
| Register pre-kindergartners for the 2023-2024 school year. | Provide online pre-registration letters to parents with directions for registering and for scheduling screening appointments | Building Principals School secretaries IT Coordinator Admin Office | February 2024 | March 2024 |
| Administer the DIAL 4 Screening Assessment | Discuss the plan with the elementary principals preschool/ child care directors Conduct DIAL 4 Screening Assessments in April/ May 2023 | Building Principals Kindergarten Teachers Support Staff | April/ May 2024 | April/ May 2024 |
| Provide Parents with DIAL 4 Score reports with explanation guide and scoring norms Offer meetings with parents to review, discuss, and interpret DIAL 4 score reports Use score reports as a component in developing classroom assignments | Mail DIAL 4 score reports with explanation guide and scoring norms Conduct meetings with parents to review, discuss, and interpret DIAL 4 score reports Construct classroom assignments | Building principals Kindergarten Teachers Building Secretaries | June 2024 | August 2024 |
| Conduct a Kindergarten Summer Tour | Invite parents and incoming Kindergarten students to the summer tour Meet with Kindergarten staff in both buildings to develop agenda and activities (principal presentation, building tour, intro to staff, craft activity, story activity, bus ride) | Elementary principals Kindergarten teachers Support staff Transportation Director | Invite sent in July 2024 Planning meeting in June 2024 | Event in August 2024 |
| Hold parent and student orientation Conduct an Early Childhood Activity Night | Prepare for parent and student orientations Plan and organize Early Childhood Activity Night - Publicize | Elementary Principals Kindergarten Teachers Transportation Department Elementary Principals Community Action Agency Early Childhood Education Committee | Invite sent with summer tour reminder in Early August 2024 Invite sent in September 2024 | Orientation on first student day August 2024 Early Childhood Activity Night in October 2024 |
| Hold a K-4 “Step-up” Activity Hold a 5th grade MS scheduling meeting Hold a 5th grade MS “move-up” day Hold a 6th grade orientation | Plan and organize a K-4 Step-up day to introduce/ transition students to next grade level Scheduling meeting with MS staff Plan and organize a “move-up” activity day for 5th grade students Plan and organize 6th grade orientation program for the summer | Elementary Principals, Counselors, and Teachers Elementary Principals MS Principal and Guidance Counselor Elementary Principals MS Principal and Guidance Counselor 6th Grade staff and students | Planning for the event to occur in April 2024 Planning for the event to occur in April 2024 Planning for the event to occur in April 2024 Planning for the event to occur in June 2024 (invite mailed to parents/students in July 2024) | Event to occur in May 2024 Event to occur in May 2024 Event to occur in May 2024 Event to occur in August 2024 |
| Conduct a Kindergarten Summer Boot Camp/ Kindergarten readiness program (TBD) | Invite students who scored below a determined percentile to a two-week summer readiness instructional program with District kindergarten staff | Elementary principals Kindergarten teachers Support staff | Invite sent in July 2024 Planning meeting in June 2024 | Event in late July or early August 2024 |